## Fos missing the deadlines
No | Factor | Contractors |  | Investors |  | supervision
|  | Iv (%) | Rank | Iv (%) | Rank | Iv (%) | Rank
1 | Shortage of material on the market | 90.53 | 1 | 91.13 | 1 | 81.48 | 6
2 | Shortage of material on the construction site | 90.15 | 2 | 87.1 | 2 | 65.74 | 16
3 | Delays in the material delivery | 89.77 | 3 | 82.26 | 4 | 87.96 | 2
4 | Financial problems during construction | 83.08 | 4 | 83.06 | 3 | 92.59 | 1
5 | poor construction site management | 81.06 | 5 | 80.65 | 5 | 87.96 | 3
6 | Delay of due payment | 76.52 | 6 | 33.06 | 33 | 38.89 | 33
7 | Inadequate material quality | 76.52 | 7 | 75 | 8 | 70.37 | 13
8 | Lack of breakdown of machinery and equipment | 76.52 | 8 | 70.97 | 12 | 75.93 | 10
9 | sluggishness in issuing permits | 76.15 | 9 | 66.13 | 18 | 51.85 | 28
10 | Subsequent design alterations | 75.76 | 10 | 67.74 | 16 | 71.3 | 12
11 | Poor assessment of time and material resources | 75 | 11 | 66.13 | 19 | 53.7 | 24
12 | Self-initiated interruption of works as requested by contractors or investors | 73.97 | 12 | 77.42 | 7 | 83.33 | 5
13 | Inadequate handling of material on the site | 73.86 | 13 | 70.16 | 13 | 65.74 | 17
14 | Insufficient training level of workers | 72.35 | 14 | 58.87 | 26 | 52.78 | 27
15 | Lack of knowledge or lack of implementation of project management | 71.97 | 15 | 70.16 | 14 | 65.74 | 18
16 | Slowness in solving problems and making decisions at the project level | 71.97 | 16 | 71.77 | 10 | 62.04 | 19
17 | Unrealistic investor requirements (deadlines) | 71.59 | 17 | 20.16 | 35 | 59.26 | 20
18 | Incomplete drawings | 71.59 | 18 | 62.1 | 25 | 52.78 | 26
19 | Poor and/or slow communication between the project participants | 71.48 | 19 | 66.13 | 20 | 66.67 | 14
20 | Errors in execution of works | 71.21 | 20 | 64.52 | 22 | 75.93 | 9
21 | Investor interfering in work | 70.83 | 21 | 29.03 | 34 | 52.78 | 25
22 | Construction site manager inexperience | 70.83 | 22 | 74.19 | 9 | 58.33 | 22
23 | Centralized decision making system in supervision | 70.45 | 23 | 70.97 | 11 | 66.67 | 15
24 | Lack of experience and/or of expertise of supervision | 70.08 | 24 | 65.32 | 21 | 37.96 | 34
25 | Incomplete documents and/or imprecise descriptions and specifications | 68.56 | 25 | 63.71 | 24 | 59.26 | 21
26 | Insufficient number of workers | 68.46 | 26 | 79.84 | 6 | 87.04 | 4
27 | Repairs and subsequent works due to poor quality and errors in construction | 67.8 | 27 | 69.35 | 15 | 74.07 | 11
28 | Self-initiated withdrawal from the project | 66.67 | 28 | 63.74 | 23 | 77.78 | 8
29 | Designer inexperience | 65.53 | 29 | 54.84 | 28 | 48.15 | 30
30 | Design errors | 64.39 | 30 | 52.42 | 30 | 42.59 | 31
31 | Stubbornness in case of a dispute between contractor, investor, and/or supervision. | 64.02 | 31 | 66.94 | 17 | 78.04 | 7
32 | Insufficient number of supervision personnel | 62.5 | 32 | 56.45 | 27 | 41.67 | 32
33 | Slowness in correcting errors in the design | 61.36 | 33 | 49.19 | 31 | 53.7 | 23
34 | Human factor (personal conflicts and dislike, corruption, political games) | 61.15 | 34 | 54.03 | 29 | 18.52 | 35
35 | Special requirements (high finish quality etc..) | 54.55 | 35 | 35.48 | 32 | 48.15 | 29

## Fos budget overrun
No | Factor | Contractors |  | Investors |  | supervision
|  | Iv (%) | Rank | Iv (%) | Rank | Iv (%) | Rank
1 | Works and procurement of materials and equipment delay (contractor responsibility) | 83.71 | 1 | 83.87 | 2 | 95.37 | 1
2 | Changes in prices of materials and equipment | 81.06 | 2 | 87.96 | 1 | 80.65 | 4
3 | Inflation (change of value of domestic currency in respect to euro) | 78.79 | 3 | 77.42 | 3 | 88.89 | 2
4 | Alterations of the project during construction (investor responsibili | 76.92 | 4 | 75.81 | 4 | 69.44 | 8
5 | Additional requirements (investor responsibility) | 76.52 | 5 | 72.58 | 7 | 66.67 | 9
6 | Poor planning and control of financial resources investment dynamics | 75.38 | 6 | 74.19 | 6 | 82.41 | 3
7 | Poor expenses record | 72.73 | 7 | 75 | 5 | 75.93 | 6
8 | Poor organization structure at the level of project | 71.59 | 8 | 62.9 | 8 | 75 | 7
9 | Incomplete design documents | 67.42 | 9 | 57.26 | 10 | 57.41 | 10
10 | Errors and flaws in the bill of quantity | 64.77 | 10 | 61.29 | 9 | 77.78 | 5